## Sheet1
Task Name,WBS Code,Assigned To,Duration (days),Predecessors,Notes
Rocky Mountain Rail Feasibility Study (Master Summary),0.0,,,,"Top-level summary row. Leave dates blank."
Project Management,1.0,,,,
Steering Committee Meetings,1.1,,,,"Monthly touchpoints per PMP."
PMC Coordination Meetings,1.2,,,,"Bi-weekly coordination."
Monthly Progress Reports,1.3,,,,"Status + invoice pack."
Project Management Plan,1.4,,,,"PMP creation & approval."
Peer Review Panels,2.0,,,,
Develop Panels,2.1,,,,"Panel composition & invites."
First Peer Review (Data/Methods),2.2,,,,"Three meetings."
Second Peer Review (Alternatives Analysis),2.3,,,,"Three meetings."
Peer Review Presentations,2.4,,,,"Six decks total."
Responses to First Peer Review,2.5,,,,"Incorporate feedback."
Responses to Second Peer Review,2.6,,,,"Incorporate feedback."
Scoping & Public Outreach,3.0,,,,
Scoping Workshops & Purpose/Need,3.1,,,,"I-70, I-25, Denver Metro."
Ongoing Public Input,3.2,,,,"Updates, meetings, media."
Policy Outreach (Workshops),3.3,,,,"I-70, I-25, Denver."
Stakeholder Outreach Approach Report,3.4,,,,"Deliverable."
Scoping Technical Report,3.5,,,,"Deliverable."
Methodology & Existing Conditions,4.0,,,,
Methodology Report,4.1,,,,"Approach for outreach, models, costs."
Market Database,4.2,,,,"O/D, Socioecon, Network, Stated Preference."
Engineering Database,4.3,,,,"ROW geometry; TRACKMAN."
Technology Database,4.4,,,,"Speed/tech options."
Property/Station Database,4.5,,,,"Stations & property values."
Existing Conditions Report,4.6,,,,"Deliverable."
Preliminary Service Scenarios,5.0,,,,
Identify Alternatives (routes/tech),5.1,,,,
Develop Initial Service Concepts,5.2,,,,"Base & improved options."
Alternatives Development Workshop,5.3,,,,"Full-day workshop."
Alternatives Development Technical Report,5.4,,,,"Deliverable."
Alternatives Analysis,6.0,,,,
Ridership Forecasts,6.1,,,,"COMPASS model."
Revenue Forecasts,6.2,,,,
Evaluation of Alternatives,6.3,,,,"Engineering & operations potential."
Operating & Capital Costs,6.4,,,,"Unit costs & assumptions."
Ridership & Revenue Report,6.5,,,,"Deliverable."
Alternatives Technical Report,6.6,,,,"Deliverable."
Feasibility Determination,7.0,,,,
Financial Analysis (Pro forma),7.1,,,,"Cash flow, NPV, IRR."
User Economic Analysis,7.2,,,,"Consumer surplus, user benefits."
Community Economic Benefits,7.3,,,,"Economic rent: jobs/income/property."
Financing & Funding Arrangements,7.4,,,,"Sources & structures."
Institutional Framework,7.5,,,,"Governance options."
Allocation of Costs & Revenues,7.6,,,,"Who pays what to whom."
Final Recommendation,7.7,,,,"Recommendation memorandum."
Documentation & Deliverables,8.0,,,,
Implementation Plan,8.1,,,,"Phasing & milestones."
Business Plan,8.2,,,,
Draft Final Report,8.3,,,,
Final Report,8.4,,,,